## Project Management Plan
Week | Task | Difficulty | Estimation
2023-09-04 | Create project plan using Excel | Easy | 1h
| Create Trello board | Easy | 1h
| Create Git repo on GitHub | Easy | 0.5h
| Setup Azure Cloud Shell | Medium | 0.5h
| Push essential files to git repo | Easy | 0.5h
| Initialize scaffolding files | Easy | 0.5h
| Test locally without error | Easy | 0.5h
| Run the source code on Cloud Shell without error | Easy | 0.5h
| Setup Github Actions | Hard | 2h
2023-09-11 | Prepare the project application with stater files | Easy | 1h
| Implement code changes | Medium | 0.5h
| Deploy to Azure App Service | Medium | 1h
| Test the application on Azure App Service | Easy | 0.5h
| Create Azure DevOps project | Easy | 0.5h
| Create Agent Pool and self-hosted agent | Hard | 3h
| Create Azure Pipeline | Medium | 2h
| Take screenshots | Easy | 1h
| Create readme file | Medium | 1h
| Create demo video | Hard | 5h
Goals
Submit final project

## Quaterly
Quarter | Goal
Q1
Q2
Q3 | Submit final project
Q4 | Enhance some features to be ready for MVP1

## Yearly
Year | Goal
2023 | Release MVP1
2024 | Release V1