## Project Management Plan
Year | Quarter | Month | Week | Task | Difficulty | Estimation (points)
2023 | Q1 | January | 2023-01-01 | Meet customer and discuss about the requirements of the project | Medium | 3
2023-01-08
|  |  | 2023-01-15 | Analyse requirements | Medium | 5
2023-01-22
|  |  | 2023-01-29 | Create business requirement document | Medium | 3
Goals
Understand the requirements and propsose BRD
|  | February | 2023-02-05
|  |  | 2023-02-12 | Create technical desgn | Hard | 5
2023-02-19
|  |  | 2023-02-26 | Technical design presentation | Medium | 3
Goals
Propose technical design
|  | March | 2023-03-05
|  |  | 2023-03-12 | Create project plan | Hard | 5
2023-03-19
|  |  | 2023-03-26 | Create Trello board | Easy | 1
Goals
Complete BRD, TDD and project planning
| Q2 | April | 2023-04-02
|  |  | 2023-04-09 | Create Git repo on GitHub | Easy | 1
2023-04-16
|  |  | 2023-04-23 | Setup Azure Cloud Shell | Easy | 1
2023-04-30
Goals
Finish environment setup
|  | May | 2023-05-07 | Push essential files to git repo | Easy | 1
2023-05-14
|  |  | 2023-05-21 | Initialize scaffolding files | Easy | 1
2023-05-28
Goals
Finish code base initialization
|  | June | 2023-06-04 | Test locally without error | Easy | 1
2023-06-11
|  |  | 2023-06-18 | Run the source code on Cloud Shell without error | Easy | 1
2023-06-25
Goals
Finish environment setup and ready for coding
| Q3 | July | 2023-07-02 | Setup Github Actions | Medium | 3
2023-07-09
|  |  | 2023-07-16 | Prepare the project application with stater files | Easy | 1
2023-07-23
|  |  | 2023-07-30 | Implement code changes | Medium | 3
Goals
Finish Github Actions setup and implemeting some base features
|  | August | 2023-08-06
|  |  | 2023-08-13 | Deploy to Azure App Service | Medium | 3
2023-08-20
|  |  | 2023-08-27 | Test the application on Azure App Service | Easy | 1
Goals
Succeed deploying on Azure App Service and ready for testing on cloud environment
|  | September | 2023-09-03
|  |  | 2023-09-10 | Create Azure DevOps project | Medium | 3
2023-09-17
|  |  | 2023-09-24 | Create Agent Pool and self-hosted agent | Hard | 5
Goals
Finish Github Actions setup for building and testing the application on cloud environment
| Q4 | October | 2023-10-01
|  |  | 2023-10-08 | Create Azure Pipeline | Hard | 5
2023-10-15
|  |  | 2023-10-22 | Take screenshots | Medium | 3
2023-10-29
Goals
Finish creating Azure Pipeline and taking screenshots for guideline document
|  | November | 2023-11-05 | Create readme file | Medium | 3
2023-11-12
|  |  | 2023-11-19 | Create demo video | Hard | 5
2023-11-26
Goals
Build guideline document and demo video
|  | December | 2023-12-03 | Desgn UI/UX | Medium | 3
2023-12-10
|  |  | 2023-12-17 | Implement Front End UI | Medium | 3
2023-12-24
|  |  | 2023-12-31 | QA | Medium | 3
Goals
Finish all features, FE implementation and QA process
Finish CI/CD pipeline
Finish all required documents and demo video
Release MVP1 of the project
Formulas:
Week = [Week, row above]+7